## Sheet1
| Three months internship | [10 empty] | Remarks
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 W10 | W11 | W12
Analysis | bar: Three months internship W1 to Three months internship W2
Design | bar: Three months internship W3 to Three months internship W4
Implementation (CUT) | bar: Three months internship W5 to Three months internship W8
Testing( ST, IT, FT, UAT)
Deployment/Demo
Progress | bar: Three months internship W1 to Three months internship W4
Waterfall model | Three months internship W1: SDLC
Ananlysis | Three months internship W1: analyze multiple Classified portals including adrevu.com and create a Requirement Specification document
Design | Three months internship W1: create high level design document (UI design, workflows, daatabase design, webservice design etc..)
Imeplementation | Three months internship W1: Coding and Unit Testing
Testing | Three months internship W1: Functionality Testing, Integration Testing, System Testing, User Acceptance Testing, Regression Testing
Deployment/Demo | Three months internship W1: Deployment/Demo

## Sheet2
Requirement no | Description | Comments/Remarks
REQ001 | Website needs to be abel to post ad
REQ002 | Website needs to have header with columns home, Post ad etc..
REQ003
REQ004
REQ005 | Website needs to be abel to post ad
REQ006
REQ007
REQ008
REQ009
REQ010
REQ011
REQ012
REQ013
REQ014
REQ015